## Timeline Visualization
Timeline Visualization Sheet by Ahmad Al-Kashef is licensed under a Creative Commons Attribution 4.0 International License.
Category | Task | Starts | Duration (wks) | Duration (dys) | Ends | Since It Started | Remaining (dys) | Status
Cat 1 | Sprint 1 | 2019-07-25 | 9 | 63 | 2019-09-26 | 0 | 63 | Doing
Cat 2 | Sprint 2 | 2019-06-15 | 4 | 28 | 2019-07-13 | 28 | 0 | Done
Cat 2 | Sprint 3 | 2019-02-02 | 4 | 28 | 2019-03-02 | 28 | 0 | Done
Cat 3 | Sprint 4 | 2019-01-26 | 8 | 56 | 2019-03-23 | 56 | 0 | Done
Cat 3 | Sprint 5 | 2019-01-08 | 4 | 28 | 2019-02-05 | 28 | 0 | Done
Cat 1 | Sprint 6 | 2019-03-30 | 8 | 56 | 2019-05-25 | 56 | 0 | Done
Cat 4 | Sprint 7 | 2019-03-30 | 4 | 28 | 2019-04-27 | 28 | 0 | Done
Cat 5 | Sprint 8 | 2019-04-30 | 4 | 28 | 2019-05-28 | 28 | 0 | Done
Cat 6 | Sprint 9 | 2019-06-01 | 4 | 28 | 2019-06-29 | 28 | 0 | Done
Cat 6 | Sprint 10 | 2019-08-01 | 10 | 70 | 2019-10-10 | 0 | 70 | To Do
Formulas:
Ends = [Starts]+([Duration (wks)]*7)
Since It Started = IF( AND((TODAY() >= [Starts]),(TODAY() < [Ends])), TODAY()-[Starts], IF(TODAY()<[Starts],0,[Duration (dys)]))
Remaining (dys) = IF(TODAY()>[Ends], 0, [Duration (dys)]-[Since It Started])
Status = IF([Remaining (dys)]<=0, "Done", IF(AND(([Remaining (dys)]=[Duration (dys)]), (TODAY() < [Starts])), "To Do", "Doing"))